## profile section
Project Name | Realestate
Application | http://realty-real-estatem1.upskills.in/wp-admin/
Module Name | Profile Section
Created By | Samudrala Bhavana
Creation Date | 2021-10-10
Reviewed By | PRODUCT OWNER
Reviewed Date
Pre Conditions | Good Network Connection
Reference | Profile Section Test plan
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Testdata | Expected Results | Actual Results | Status | Comments (if any) | Conclusion
TS_01 | Verify Whether Profile Section is displaying on the page after entering the login credentials | TC_01 | Check response after entering login credentials the home page is dislaying or not | 1. Enter the Valid URL of the Website 2. Click on the Enter Key 3. Enter the Valid Login Credentails 4. Click on sign in button 5. Home page will be displayed | 1.Realesate website URL : http://realty-real-estatem1.upskills.in/wp-admin/profile.php 2.Login Credentials: Username : admin Password : admin @123 | After entering login credentials home page shoud display | After entering login credentials home page is opened | pass | N/A | N/A
|  | TC_02 | Check response after opening home page is Profile section is displaying or not | 1. Home Page will be Opened 2. Profile section will display |  | After opening home page ,profile section should display | After opening home pade,profile section is displayed | pass | N/A | N/A
|  | TC_03 | Check whether the position of Profile section is present at top right side corner of the home page | 1. Home page will be Opened 2. Profile section will display at top right side |  | Profile section should present at top right side corner of the page | profile section is present at top right side corner of the page | pass | N/A | N/A
TS_02 | Verify Profile section is displayed with Admin name or not | TC_04 | Validate the profile section is displaying with Admin Name | 1. Home page will be Opened 2. Profile section will display at top right side 3.Profile section logo will be displayed with Admin name | Admin Name : Bhavana Samudrala | Profile section should display with admin anme | profile section is displayed with admin name | pass | N/A | N/A
TS_03 | Verify that Placing Cursor on the Profile Section will display Sub options | TC_05 | Check whether pointing cursor on profile section showing profile picture logo | 1. Log in to the page 2.point a cursor on Profile Section | Login Credentials: Username: admin Password: admin@123 | pointing cursor on profile section should display picture logo | pointing cursor on profile section is displayed picture logo | pass | N/A | N/A
|  | TC_06 | Check whether pointing cursor on profile section showing admin name | 1. Log in to the page 2.point a cursor on Profile Section |  | pointing cursor on profile section should dispay admin name | pointing cursor on profile section is displayed admin name | pass | N/A | N/A
|  | TC_07 | Check whether pointing cursor on profile section showing the User name as Admin | 1. Log in to the page 2.point a cursor on Profile Section |  | pointing cursor on profile section should show the user name as admin | pointing cursor on profile section is displayed user name as admin | pass | N/A | N/A
|  | TC_08 | Check whether pointing cursor on profile section showing EDIT MY PROFILE option | 1. Log in to the page 2.point a cursor on Profile Section |  | pointing cursor on profile section should display' edit my profile' option | pointing cursor on profile section is displayed with 'edit my profile' option | pass | N/A | N/A
|  | TC_09 | Check whether pointing cursor on profile section showing LOG OUT option | 1. Log in to the page 2.point a cursor on Profile Section |  | pointing cursor on profile section should display LOG OUT option | pointing cursor on profile section is displayed with LOG OUT option | pass | N/A | N/A
TS_04 | Verify that clicking on Profile Section will redirect to Profile Page | TC_10 | Check whether Clicking on Profie section will redirect to profile page | 1. Log in to the page 2. click on profile section | Login Credentials: Username: admin Password: admin@123 | Clicking on profile section should redirect to profile page | Clicking on profile section is redirected to profile page | pass | N/A | N/A
|  | TC_11 | Check clicking on Edit My Profile option will redirect to Profile page | 1.Log in to the page 2. Click on Edit My Profile option |  | Clicking on Edit MY Profile option should redirect to profile page | Clicking on Edit My Profile option is redirected to profile page | pass | N/A | N/A
|  | TC_12 | Check clicking on Admin Name will redirect to profile Page | 1.Log in to the page 1. Click on Admin name |  | Clicking on Admin name should redirect to profile page | Clicking on Admin name is redirected to profile page | pass | N/A | N/A
TS_05 | Verify the Details of the Profile section which has to be updated | TC_13 | Check whether profile page contains the first name and last name columns | 1.Click on profile section or 2.Click on Edit My Profile Option or 3. Click on Admin name | N/A | Profile page should contain the first name and last name | Profile page is displayed with first name and last name | pass | N/A | N/A
|  | TC_14 | Check whether we can add the nickname in the profile page | 1.Click on profile section or 2.Click on Edit My Profile Option or 3. Click on Admin name | N/A | Profile page should contain the Nick name | Profile page is displayed with Nick name | pass | N/A | N/A
|  | TC_15 | Check the profile page whether it contains contact information or not | 1.Click on profile section or 2.Click on Edit My Profile Option or 3. Click on Admin name | N/A | Profile page should contain contact information | Profile page is displayed with contact information | pass | N/A | N/A
|  | TC_16 | check that the profile page contains the email id column which is mandatory to validate | 1.Click on profile section or 2.Click on Edit My Profile Option or 3. Click on Admin name | N/A | Profile page should contain the email ID column | Profile page is displayed with Email ID column | pass | N/A | N/A
|  | TC_17 | Check the profile page whether it contains Website link option | 1.Click on profile section or 2.Click on Edit My Profile Option or 3. Click on Admin name | N/A | Profile page should contain the website links | Profile page is displayed with website links | pass | N/A | N/A
|  | TC_18 | Check whether profile page has the mobile number column | 1.Click on profile section or 2.Click on Edit My Profile Option or 3. Click on Admin name | N/A | Profile page should contain the Mobile number column | Profile page is displayed with mobile number column | pass | N/A | N/A
|  | TC_19 | Check whether we can add social media links in the profile page | 1.Click on profile section or 2.Click on Edit My Profile Option or 3. Click on Admin name | N/A | Profile page should contain social media links | Profile page is displayed with social media links | pass | N/A | N/A
|  | TC_20 | Check whether we can add Biographical information in the profile page | 1.Click on profile section or 2.Click on Edit My Profile Option or 3. Click on Admin name | N/A | Profile page should contain the Biographical information | Profile page is displayed with biographical information | pass | N/A | N/A
|  | TC_21 | Check whether we can update profile picture in profile page | 1.Click on profile section or 2.Click on Edit My Profile Option or 3. Click on Admin name | N/A | Profile page should contain the profile picture upload option | Profile page is displayed with profile picture upload option | pass | N/A | N/A
|  | TC_22 | Check whether we can change the password settings in profile page | 1.Click on profile section or 2.Click on Edit My Profile Option or 3. Click on Admin name | N/A | Profile page should contain the password changing settings | Profile page is displayed with password settings | pass | N/A | N/A
|  | TC_23 | Check whether we can update Customer billing address details | 1.Click on profile section or 2.Click on Edit My Profile Option or 3. Click on Admin name | N/A | Profile page should contain the customer billing address details | Profile page is dispalyed with customer shipping address details | pass | N/A | N/A
|  | TC_24 | Check whether we can update Customer shipping address details | 1.Click on profile section or 2.Click on Edit My Profile Option or 3. Click on Admin name | N/A | Profile page should contain the customer shipping address details | Profile page is displayed with customer shipping address details | pass | N/A | N/A
TS_06 | Verify the functionality of admin color scheme in profile page | TC_25 | Check whether admin colour scheme is used to change the colour settings of the whole page | 1. Click on profile section 2.Click on admin colour scheme options | N/A | Admin colour scheme will used to change the color settings of the page | Admin colour scheme is used to change the color settings of the page | pass | N/A | N/A
|  | TC_26 | Check whether admin color scheme options are available in radio buttons | 1. click on profile section 1.Click on admin colour scheme options | N/A | admin color scheme options shoud display in radio buttons | admin color scheme options is displayed in radio buttons | pass | N/A | N/A
|  | TC_27 | Check whether there is default colour setting in colour scheme | 1. click on profile section 2. click on admin colour scheme options 3.click on default colour option | N/A | there should be default colour setting option in color scheme | there is a default colour setting option in color scheme | pass | N/A | N/A
|  | TC_28 | Check whether there is many other colours in colour scheme | 1.click on profile section 2. click on admin colour scheme options 3.click on many other colour options present there | N/A | there should be many other colours in colour scheme | there is many other colours in colour scheme | pass | N/A | N/A
TS_07 | Verify whether Username is changing or not when you already log in as admin/user | TC_29 | Check the Username when you login as user | 1. click on profile section 2. Click on username | N/A | Username should be user | Username is user | pass | N/A | N/A
|  | TC_30 | Check the username when you login as Admin | 1. click on profile section 2. Click on username | N/A | username should be admin | username is admin | pass | N/A | N/A
|  | TC_31 | Check the username is displaying below Admin name | 1. click on profile section | N/A | Username will be admin | username is admin | pass | N/A | N/A
|  | TC_32 | Check whether username is changing or not in profile page when you log in as Admin | 1. click on profile section 2. Click on username | N/A | username will not be changed | username is not changing | pass | N/A | N/A
|  | TC_33 | Check whether username is changing or not in profile page when you log in as user | 1. click on profile section 2. Click on username | N/A | username will not be changed | username is not changing | pass | N/A | N/A
TS_08 | Verify the function of "Display name Publicly as" option by giving Admin name | TC_34 | Check the option whether we can give admin name here | 1. click on Display Name Publicly as option 2.Enter Admin name | Admin Name : Bhavana Samudrala | We can give admin name here | We can give admin name here | pass | N/A | N/A
|  | TC_35 | Check whether if we give any name in this option will display on the profile section or not | 1. click on Display Name Publicly as option 2.Enter Admin name |  | It should display on profile section | It is displayed on profile section | pass | N/A | N/A
|  | TC_36 | Check whether this option contains existing admin names in drop down buttons | 1. click on Display Name Publicly as option 2.Enter Admin name 3. click on drop down button |  | It should contain drop down button with existed admin names | It is contained drop down button with existed admin names | pass | N/A | N/A
|  | TC_37 | Check the name mentioned in this option will aslo display on the main page of the Realestate | 1. click on realestate website 2. click on enter key | N/A | It will display on main page of the realestate | It is displayed on main page of the realestate | pass | N/A | N/A
TS_09 | Verify all options are present in Contact Info is related to contact information | TC_38 | Check whether Email is asked to verify the mail | 1. Go to contact info section 2.click on email address 3. Enter the Valid Email id 4. Click on Enter key | Valid Email id : samudrala124@gmail.com | Email will be asked to verify the mail | Email is asked to verify the mail | pass | N/A | N/A
|  | TC_39 | Check whether website link is asked in contact information | 1. Go to contact info section 2.click on website option 3. Enter the Website link | website link: http://realty-real-estatem1.upskills.in/ | website link will be asked in contact information | website link is asked in contact info | pass | N/A | N/A
|  | TC_40 | Check whether phone number is visible in contact information | 1. Go to contact info section 2.click on phone number 3. Enter phone number 4. click on Enter key | phone number: 7788994422 | phone number will be asked in contact info | phone number will be asked in contact info | pass | N/A | N/A
|  | TC_41 | check whether linked in id is asked in contact info | 1. Go to contact info section 2.click on linked in option 3. Enter linked in id 4. click on Enter key | Linked in ID : | Linked in Id will be asked in contact info | Linked in Id is asked in contact info | pass | N/A | N/A
|  | TC_42 | check whether twitter id is asked in contact information | 1. Go to contact info section 2.click on twitter id option 3. Enter twitter id 4. click on Enter key | Twitter ID: | Twitter Id will be asked in contact info | Twitter Id is asked in contact info | pass | N/A | N/A
|  | TC_43 | check whether Facebook id is asked in contact information | 1. Go to contact info section 2.click on facebook option 3. Enter facebok id or facebook URL 4. click on Enter key | Facebook ID: | Facebook Id will be asked in contact info | Facebook Id is asked in contact info | pass | N/A | N/A
TS_10 | Verify how email address will be updated for admin profile | TC_44 | Check whether email id is mandatory to update admin profile | 1.Enter contact info section 2. click on email id option | N/A | Email ID will be mandatory to update admin profile | Email ID is mandatory to update admin profile | pass | N/A | N/A
|  | TC_45 | Check the response if we give existed mail id | 1. Enter contact info section 2. click on email id option 3. enter already used mail id | Existed mail ID: samudralabhavana2@gmail.com | It will be displayed with a message that it is already used mail id | It is displayed with a message that it is already used mail id | pass | N/A | N/A
|  | TC_46 | Check the response if you give invalid mail id | 1. click on email id option 2. enter invalid mail id | Invalid Mail ID: XXXXX@gmail.com | It will be displayed with a message that it is invalid mail id | It is displayed with a message that it is invalid mail id | pass | N/A | N/A
|  | TC_47 | Check response after entering valid mail id | 1. click on email id option 2. enter valid mail id | Valid Email id : samudrala124@gmail.com | It should be send mail for verification | verification mail is not received | fail | DEFECT | Verification mail is not received
|  | TC_48 | Check whether you are getting verification mail to your mentioned mail id | 1. click on email id option 2. enter valid mail id 3. check your mails | N/A | It should get the verification mail | verification mail is not received | fail | DEFECT | verification mail is not received
|  | TC_49 | Check the response if your email is not validated | 1. check the page | N/A | It should give a message that: There is pending change in your mail | a message that: There is pending change in your mail | pass | N/A | N/A
|  | TC_50 | Check whether there is any instructions given if email is not updated | 1. check the page | N/A | There is a instruction : Your email address has not been updated | There is a instruction : Your email address has not been updated | pass | N/A | N/A
TS_11 | Verify the functionality to upload a profile picture through Gravator site | TC_51 | Check whether there is profile picture section to upload picture there | 1. click on profile section 2.click on upload picture | N/A | There should be profile picture section to upload picture | There is a profile picture section to upload picture | pass | N/A | N/A
|  | TC_52 | Check whether is there is no other option to upload a profile picture other than gravator | 1. check gravator link | N/A | There will be no other option to upload picture | There is no other option to upload picture | pass | N/A | N/A
|  | TC_53 | Check whether gravator link is given or not to upload a picture | 1.click on gravator link | N/A | There should be gravator link | There is a gravator link | pass | N/A | N/A
|  | TC_54 | Check the response after clicking in gravator | 1.click on gravator link | N/A | It should redirect to gravator account | It is redirecting to gravator account | pass | N/A | N/A
|  | TC_55 | Check gravator is asked to create account in gravator | 1.click on gravator link 2. sign up in gravator account | First name: Bhavana Last name: Samudrala email: samudralabhavana2@gmail.com | It will be asked to create account in gravator | It is asked to create account in gravator | pass | N/A | N/A
|  | TC_56 | Check whether garavtor is linked with word press | 1. sign in gravator account 2. check the word press account | N/A | It will be linked with word press account | It is linked with word press account | pass | N/A | N/A
|  | TC_57 | Check word press also asked to create account in it | 1. Sign up in word press account | First name: Bhavana Last name: Samudrala email: samudralabhavana2@gmail.com | It will be asked to create account in word press | It is asked to create account in word press | pass | N/A | N/A
|  | TC_58 | Check the response after uploading a picture there | 1. upload picture in gravator 2. upload picture in word press | N/A | It should be taken as uploaded | It is taken | pass | N/A | N/A
|  | TC_59 | check whether uploaded picture is displaying on profile page or not | 1. check profile page | N/A | It should be displayed on profile page | It is not displayed on profile page | fail | DEFECT | Profile picture is not displaying on the profile page
TS_12 | Verify the functionality of Creating a new password | TC_60 | Check whether there is option to generate password | 1. click on profile section 2. click on generate pasword | N/A | There should be a option to generate password | There is a option to generate password | pass | N/A | N/A
|  | TC_61 | Check the hide and cancel option to hide password and cancel password | 1. click on hide option 2. click on cancel option | N/A | The hide and cancel options should be used to hide&cancel password | The hide and cancel options is used to hide&cancel password | pass | N/A | N/A
|  | TC_62 | check whether it is showing the given password is strong or medium or weak | 1. click on Generate password option 2. Enter a Password | Password: admin@123 | The given password will be weak | The given password is weak | pass | N/A | N/A
|  | TC_63 | check the response on giving strong password | 1. click on Generate password option 2. Enter a Password | password: Capgemini@123 | The given password will be strong | The given password is strong | pass | N/A | N/A
|  | TC_64 | check the response on giving medium password | 1. click on Generate password option 2. Enter a Password | Password: Bhavana1 | The given password will be medium | The given password is medium | pass | N/A | N/A
|  | TC_65 | check the response on giving weak password | 1. click on Generate password option 2. Enter a Password | Password: admin@123 | The given password will be weak | The given password is weak | pass | N/A | N/A
TS_13 | Verify whether the sessions is used to logout everwhere else except in the system we used | TC_66 | Check whether session option is used for security reasons | 1. check the sessions | N/A | Session should be for security reasons | Session is be for security reasons | pass | N/A | N/A
|  | TC_67 | check the option Log Out Everywhere else present or not | 1. Check the sessions 2.check the Log Out Everwhere else option | N/A | Log Out Everywhere else option should present | Log Out Everywhere else option is present | pass | N/A | N/A
|  | TC_68 | Check the response after clicking on log out everwhere else option | 1. check the sessions 2.click on logout everywhere else option | N/A | It should logout from the page everyother device | It is logged out from the page everyother device | pass | N/A | N/A
|  | TC_69 | check whether it gives any message after clicking on it | 1. check the sessions 2.click on logout everywhere else option | N/A | Message: you are logged out everywhere else except here | Message: you are logged out everywhere else except here | pass | N/A | N/A
TS_14 | VerifY all the options are prsent in customer billing address is related to billing address | TC_70 | Check whether first name and last name is asked in the address details | 1. check customer billing addres section 2.Enter First name 3. Enter last name | First name: Bhavana Last name: Samudrala | First name and Last name will be asked | First name and Last name is asked | pass | N/A | N/A
|  | TC_71 | Check whether company address is asked or not | 1. check customer billing addres section 2.Enter company address | Company address: pune | Company address will be asked | Company address is asked | pass | N/A | N/A
|  | TC_72 | Check whether billing address is given in customer billing address | 1. check customer billing adress section 2. Enter billing address | Billing address: warangal | Billing address will be asked | Billing address is asked | pass | N/A | N/A
|  | TC_73 | Check whether city is asked in customer billing address | 1. Enter city | city : warangal | city will be asked | city is asked | pass | N/A | N/A
|  | TC_74 | Check whether postcode is visible in customer billing address | 1. Enter post code | postcode: 12345 | postcode will be asked | postcode is asked | pass | N/A | N/A
|  | TC_75 | Check whether country is asked in billing address details with dropdown box contains all the list of countries | 1. select and enter country name from dropdown button | country: india | country drop down button should given with country names | country drop down button is given with country names | pass | N/A | N/A
|  | TC_76 | Check whether state is asked with dropdown button to select a state | 1. select and enter state name from dropdown button | state : telangana | state drop down button should given with state names | state drop down button is given with state names | pass | N/A | N/A
|  | TC_77 | Check whether phone number and email address are asked in customer billing address | 1. Enter phone number 2.enter email address | phone number:7788994422 email: samudralabhavana2@gmail.com | phone number and email ID will be asked | phone number and email ID is asked | pass | N/A | N/A
TS_15 | Verify all the options are prsent in customer shipping address is related to shipping address | TC_78 | Check whether the options in customer billing address is same as in customer shipping address | 1.check customer shipping address section | N/A | Customer billing adress details should be same as customer shipping address | Customer billing adress details is same as customer shipping address | pass | N/A | N/A
|  | TC_79 | check whether there is a option to copy same address from billing address details | 1.check customer shipping address section | N/A | There should be a option to copy same address from billing address | There is a option to copy same address from billing address | pass | N/A | N/A
|  | TC_80 | check the response on clicking the copy billing address option | 1.check customer shipping address section 2. click on copy billing address | N/A | copy address from billing to shipping | copy address from billing to shipping | pass | N/A | N/A
TS_16 | Verify the working functionality of update profile button | TC_81 | check clicking on update profile button is used to update profile or not | 1. check update profile button | N/A | Updates profile of the admin | Updates profile of the admin | pass | N/A | N/A
|  | TC_82 | Check what happens if we didn’t click on the update profile | 1. click on update profile button | N/A | It wont update the admin details | It wont update the admin details | pass | N/A | N/A
|  | TC_83 | check the response if we didn’t fill any details | 1. click on update profile button | N/A | It should ask to fill the details on mandatory options | It is asked to fill the details on mandatory options | pass | N/A | N/A
|  | TC_84 | check response if we fill half of the details | 1. click on update profile button | N/A | It will update | It is updated | pass | N/A | N/A
|  | TC_85 | check response if we didn’t fill mandatory details | 1. click on update profile button | N/A | It ask to fill the details | It is asked to fill the details | pass | N/A | N/A
|  | TC_86 | check response after updating the profile | 1. click on update profile button | N/A | Details will be updated | Details will be updated | pass | N/A | N/A
TS_17 | Verify the working functionality of Help dropdown | TC_87 | Validate after clicking on Help option is it working or not | 1. click on Help dropdown button | N/A | It should be working | It is working | pass | N/A | N/A
|  | TC_88 | Check response after clicking on the help button is it display relavant content or not | 1. click on Help dropdown button | N/A | It should display relevant data | It is showing relevant data | pass | N/A | N/A
|  | TC_89 | Check whether it is showing the help desk links | 1. click on Help dropdown button | N/A | It should show the help desk links | It is showing the help desk links | pass | N/A | N/A
|  | TC_90 | Check whether there is a option when we find a bug | 1. click on Help dropdown button | N/A | It should be option to raise a bug | There is a option to raise a bug | pass | N/A | N/A
|  | TC_91 | Check whether there is support forums to be filled | 1. click on Help dropdown button | N/A | it should have support forumns | it had support forumns | pass | N/A | N/A
|  | TC_92 | Check whether it is showing relevant links to fix a error | 1. click on Help dropdown button | N/A | It should show relevant links to fix a error | It is showing relevant links to fix a error | pass | N/A | N/A
TS_18 | Verify the working functionality of LOG OUT option in profile section | TC_93 | check cliking on LOG OUT will be used to logout from the website | 1. click on LOG OUT option | N/A | We should logged out from the page | We are logged out from the page | pass | N/A | N/A